## Scenario Details
Scenario | Requirement | Status | Note
S1 Case-based routing | Email interactions tied to Salesforce cases | Done | ordersuccess@: real Connect email contact routed + logged as EmailMessage on the Case (full HTML body); taskdemo@: Task tagged caseId; new inquiry auto-creates a Case.
S1 Case-based routing | Auto-identify Salesforce Case IDs in threads | Done | Regex on subject (Case #NNNNN).
S1 Case-based routing | Routing based on Salesforce Case Owner | Done | Live SOQL lookup -> owner's agent.
S1 Case-based routing | Sync of ownership changes SF <-> platform | Done | Every reply resolves the current owner live; SF is the single source of truth.
S1 Case-based routing | Preservation of email thread continuity | Done | Every message logged on one Case; native email shows the full quoted thread; all replies route to the same case/owner.
S1 Case-based routing | Success: no manual reassignment | Done
S1 Case-based routing | Success: routing leverages Salesforce data | Done | Live Client-Credentials SOQL.
S1 Case-based routing | Success: ownership changes reflected immediately | Done | On both reply paths.
S1 Case-based routing | Success: customer stays with the specialist | Done | Routes to the owner's agent.
S2 Shared mailbox | Multiple agents on a common address | Done | Shared ordersuccess@ccaas.evolvity.com.
S2 Shared mailbox | Visibility into assigned owner | Done | ownerName on contact/Task + audit table.
S2 Shared mailbox | Routing of replies to original owner | Done | Remembered owner; case's current owner re-read live.
S2 Shared mailbox | Ownership transfer workflows | Done | Salesforce Change Owner (system of record); routing honors it live. Connect transfer = collaboration, not ownership.
S2 Shared mailbox | Supervisor reassignment capabilities | Done | Supervisor reassigns in SF -> next reply routes to the new owner.
S2 Shared mailbox | Success: seamless to customer | Done | Customer emails the shared address.
S2 Shared mailbox | Success: ownership visible & auditable | Done | Attributes + email-routing-log.
S2 Shared mailbox | Success: continuity maintained | Done | Every reply routes to the thread's current owner.
S3 Hybrid routing | Traditional ACD routing | Done | Queues + routing profiles auto-assign; owner-targeted + shared fallback.
S3 Hybrid routing | Shared queue visibility | Done | Native real-time metrics; dedicated agent pull view not configured.
S3 Hybrid routing | Agent self-selection of work items (cherry-pick) | Done | ACD push today; manual-select/pull queue not built.
S3 Hybrid routing | Supervisor controls governing cherry-pick | Done | Rides on the self-selection setup. (remove manual assignment from agent/owner profile)
S3 Hybrid routing | Mixed routing strategies simultaneously | Done | ACD built; per-team auto+pull mix is the delta.
S3 Hybrid routing | Success: different departments, different models | Done | ACD per team; add a pull queue for cherry-pick teams.
S3 Hybrid routing | Success: select work without duplicate effort | Done
S3 Hybrid routing | Success: supervisors keep governance | Done
S4 Outbound tracking | Agent-initiated outbound email | Done | Native email channel; reply/initiate from ordersuccess@ (Initiate email permission on).
S4 Outbound tracking | Tracking of outbound-only interactions | Done | Connect records the outbound reply/email as a contact.
S4 Outbound tracking | Reporting on outbound communications | Done | Native metrics + contact search; dedicated outbound-only report is polish.
S4 Outbound tracking | Visibility into agent productivity | Done | Native agent metrics; outbound-specific report is polish.
S4 Outbound tracking | Audit and review capabilities | Done | email-routing-log + Connect contact records.
S4 Outbound tracking | Success: outbound reportable / leadership visibility | Done | Tracked + in dashboards/contact search; tailored leadership report is polish.
S5 Customer/account 360 | Customer view: open emails | Done | EmailMessages on the contact/case; contact Activity.
S5 Customer/account 360 | Customer view: historical emails | Done | Case + contact history.
S5 Customer/account 360 | Customer view: open Salesforce cases | Done | Contact -> Cases related list.
S5 Customer/account 360 | Customer view: interaction timeline | Done | Contact Activity timeline.
S5 Customer/account 360 | Customer view: previous communications | Done
S5 Customer/account 360 | Account view: activity from multiple contacts | Done | Roll-up shows contacts' activity (org setting on).
S5 Customer/account 360 | Account view: open cases across the account | Done | Account -> Cases related list.
S5 Customer/account 360 | Account view: open interactions across the account | Done | Via account cases/activity.
S5 Customer/account 360 | Account view: assigned ownership | Done | Case Owner.
S5 Customer/account 360 | Duplicate-work alerts |  | 360 is visible but no proactive alert.
S5 Customer/account 360 | Success: agents understand history | Done | Via the 360 + screen-pop.
S5 Customer/account 360 | Success: duplicate effort minimized | Done | Visible via the 360; active alerting not built.
S5 Customer/account 360 | Success: consistent CX across teams | Done | Same case/contact/account for everyone.
S6 CRM-data routing | Route by Salesforce Case Owner | Done | Core routing (live SOQL -> owner's agent).
S6 CRM-data routing | Route by Account Ownership | Partial | Account linked; routing by account owner reuses the Lambda pattern - not built.
S6 CRM-data routing | Route by Customer/Product/Order/Case Type/Business Rules |  | Lambda can query any Salesforce field; currently keys on Case Owner.
S6 CRM-data routing | Success: multiple variables simultaneously | Partial | Lambda supports it; currently owner-based.
S6 CRM-data routing | Success: admin-maintainable routing | Partial | Today via code/tfvars; a DynamoDB rules table would make it admin-editable.
S6 CRM-data routing | Success: minimal custom development | Partial | Engine + mapping in place; per-rule config is the delta.
S7 Productivity/collab | Unified agent desktop | Partial | Connect agent workspace + Detail-view screen-pop (SF Case link/owner); full SF unification via CTI is an enhancement.
S7 Productivity/collab | S7 Productivity/collab | Partial | Native email channel supports quick responses/templates; not curated for this demo.
S7 Productivity/collab | Address book integration |  | Not built.
S7 Productivity/collab | Knowledge search |  | Amazon Q / knowledge base.
S7 Productivity/collab | Multi-session handling | Done | Concurrent contacts (TASK + EMAIL concurrency).
S7 Productivity/collab | Internal collaboration | Done | Quick connects - transfer/consult; verified on the native email channel.
S7 Productivity/collab | Shared drafts |  | Not built.
S7 Productivity/collab | Expert consultation workflows | Partial | Transfer/consult via quick connect; a formal consult workflow is more.
S7 Productivity/collab | Success: reduced effort / faster / consistency | Partial | Collaboration + multi-session + screen-pop now; templates more.
S8 AI / future-state | AI-generated email drafts | Future | Amazon Q in Connect.
S8 AI / future-state | Suggested responses | Future | Amazon Q in Connect.
S8 AI / future-state | Agent assist | Future | Amazon Q in Connect.
S8 AI / future-state | Knowledge retrieval | Future | Amazon Q + knowledge base.
S8 AI / future-state | Automated categorization | Future | Bedrock/Comprehend or Connect rules.
S8 AI / future-state | Automated prioritization | Future | Routing rules + AI signals.
S8 AI / future-state | Customer sentiment analysis | Future | Contact Lens / Comprehend.

## Final Demo Exercise
Step | Action | Status | Note
1 | Customer sends an inquiry | Done | Inbound email received by SES.
2 | Salesforce case is created or identified | Done | Identified via Case #; a new inquiry auto-creates a Case and routes to its owner.
3 | Agent responds from a shared mailbox | Done | ordersuccess@ on Connect native email; agent replies natively. Hybrid (taskdemo@ = Task path).
4 | Customer replies | Done | Inbound reply received.
5 | Platform identifies the Salesforce Case ID | Done | Regex on subject.
6 | Email routes to the assigned owner | Done | Owner-targeted routing to the owner's agent.
7 | Agent opens the interaction and sees the customer 360 | Done | Detail-view screen-pop on accept (clickable Case link + owner) + email logged to the Case with full HTML body; Case linked to Contact/Account.
8 | Agent collaborates with another employee | Done | USER quick connects (Transfer-to-<agent>); verified on the native email channel.
9 | Agent sends a response | Done | Native email reply delivered to external inbox (SPF+DKIM pass); logged to the SF Case with full HTML body.
10 | Interaction is tracked, reported, and auditable | Done | Native Connect dashboards + contact search + email-routing-log.
11 | Supervisors review routing / ownership / metrics | Done | Supervisor user (CallCenterManager) + dashboards; ownership in email-routing-log + SF case history.

## Scenario Summary
# | Scenario | Status | Notes
1 | Salesforce case-based email routing | Done | All requirements met (native email on ordersuccess@).
2 | Shared mailbox with individual ownership | Done | All requirements met.
3 | Hybrid routing (ACD + agent self-selection) | Partial | ACD built; agent self-selection/cherry-pick + governance not yet.
4 | Outbound email tracking & visibility | Partial | Outbound built on the native email channel; dedicated outbound-only reporting is polish.
5 | Customer / account-level visibility | Partial | Customer + account 360 built (+ screen-pop); duplicate-work alerts not yet.
6 | Complex routing using CRM data | Partial | Routing engine built (by Case Owner); extends to any CRM field via same Lambda.
7 | Agent productivity & collaboration | Partial | Collaboration/consult + multi-session + screen-pop built; templates/knowledge/drafts more.
8 | AI & future-state |  | Future-state roadmap via Amazon Q in Connect.